|  |  |
| --- | --- |
| **IAS.C** | **REQUEST FORM FOR CREATION OF AN AUDIT PROJECT IN TEAM MATE** |

Last update: 01/2017

|  |  |
| --- | --- |
| **Project Reference[[1]](#footnote-1)** | IAS.C1-2018-DG X-00n |
| **Project Title** | IAS Audit on CEF in DG X |
| **Name of DG/Agency** | DG X |
| **Audit Report Year** | 2018 |
| **Audit Category** | C1 |
| **Audit Type** | Comprehensive engagement |
| **Audit Origin** | Risk assessment |
| **Audit Schedule** | 2018 |
| **Audit Security** | Standard |
| **Scheduled person-days** | 150 |
| **Name of Audit Manager** | <Name1>  |
| **Name of Audit Lead** | Mirco BARBERO  |
| **Names of Auditors[[2]](#footnote-2)** | <Name2 > |
| **Estimated Announcement Letter** | 9/03/2018 |
| **Estimated Audit Start** | 19/03/2018 |
| **Estimated EPM[[3]](#endnote-1)** | 25/05/2018 |
| **Estimated End of Preliminary Survey** | 06/06/2017 |
| **Estimated FVT/ADAR @ Director** | 21/09/2017 |
| **Estimated FVT/ADAR @ QA** | 28/09/2017 |
| **Estimated FVT/ADAR @ Auditee** | 05/10/2017 |
| **Estimated End of Fieldwork/FVT**  | 19/10/2017 |
| **Estimated Draft Report**  | 26/10/2017 |
| **Estimated Auditor's Comments to Draft Report**  | 19/11/2017 |
| **Estimated Final Report**  | 26/11/2017 |
| **Estimated Auditee's Action Plan 2** | 12/12/2017 |
| **Estimated IAS Reply to Action Plan 2** | 17/12/2017 |

|  |  |  |
| --- | --- | --- |
|  | Date | Signature |
| Responsible Auditor: Mirco Barbero |  |  |
| Audit Manager: <Name1> |  |  |

1. To be completed by the Planning Assistant [↑](#footnote-ref-1)
2. Please add the secretary of the unit as an auditor. [↑](#footnote-ref-2)
3. [↑](#endnote-ref-1)