## Foaie1
ANNEX 2
PLANNING ROADMAP
Engagement Planning | [5 empty] | Action performed? |  |  | Information to be used for EPM Chapter Nº | WP Ref
[6 empty] | Y | N | NA
PRELIMINARY SURVEY | 1. | Identify why the mission was included in annual plan | [6 empty] | 1
| 2. | Identify changes that occurred after the risk analysis performed for annual planning | [6 empty] | 4.2
| 3. | Identify the expectations of the main stakeholders | [6 empty] | 5.1
| 4. | Identify prior audits | [6 empty] | 4.1
| 5. | Identify strategies - objectives - risks of the audited area | [6 empty] | 2.1, 2.2, 3
|  | 5.1. | understand the: mission, vision, objectives of the entity, risk, risk appetite, control environment, governance structure, risk management process; legal and procedural framework | [5 empty] | 2.1, 2.2, 3
|  |  | 5.1.1. | identify and understand mission, strategic objectives, Key Performance Indicators, legal and procedural base |  |  |  |  | 2.1, 2.2, 3
|  |  |  | 5.1.1.1. | review the organizational structure, management roles, management reports, operating procedures and legal base, KPIs |  |  |  | 2.1, 2.2, 3
|  |  |  | 5.1.1.2. | perform interviews with the management of the audited area to understand the strategies and objectives |  |  |  | 2.1
|  |  |  | 5.1.1.3. | review the strategy papers, planning documentation, budgets, minutes of the meetings |  |  |  | 2.1
|  |  | 5.1.2. | identify and understand risks and controls of the area to be audited |  |  |  |  | 2.2, 4.3
|  |  |  | 5.1.2.1. | from the documents under point 5.1.1. identify and independently assess the risks |  |  |  | 2.2, 4.3
|  |  |  | 5.1.2.2. | identify if new risks were introduced by the new processes or new conditions |  |  |  | 2.2, 4.3
|  |  | 5.1.3. | assess if the risks are managed to a tolerable level |  |  |  |  | 2.2, 4.3
|  |  |  | 5.1.3.1. | review the risk management process |  |  |  | 2.2, 4.3
|  | 5.2. | develop a risk and control matrix or review of the existing one | [5 empty] | 2.2, 4.4
|  | 5.3. | gather information on policies and procedures applicable of the audited area | [5 empty] | 2.2
|  | 5.4. | understand the IT systems used | [5 empty] | 2.2
|  | 5.5. | identify the source, types and reliability of information used in the audited process | [5 empty] | 2.2
|  | 5.6. | obtain and review the results of prior audits | [5 empty] | 4.1
| 6. | Identify the adding value opportunities | [6 empty] | 5.2
|  | 6.1. | use professional judgement, knowledge and experience to identify opportunities for making significant improvements to the organization's governance, risk management and control processes | [5 empty] | 5.2
OBJECTIVES SETTING | 7. | Establish the Engagement Objectives | [6 empty] | 5.1
|  | 7.1. | use the results of "Preliminary Survey" and annual internal audit plan to attain a complete understanding of why the engagement is being conducted and what the organizations want to achieve | [5 empty] | 5.1
|  | 7.2. | understand the short-term and long-term goals of the auditee, as well as the inputs and outputs and applicable procedures | [5 empty] | 5.1
|  | 7.3. | identify and understand the expectations of the senior management, the board and stakeholders | [5 empty] | 5.1
|  | 7.4. | formulate the preliminary objectives of the engagement | [5 empty] | 5.1
|  | 7.5. | identify if the risk assessment was performed during the preliminary survey phase and use the results. If not, perform risk analysis | [5 empty] | 5.1
|  | 7.6. | further enhance the preliminary objectives considering the risk analysis results. The objectives should reflect what the management is specifically attempting to accomplish | [5 empty] | 5.1
DEFINING AUDIT SCOPE | 8. | Set up the Engagement Scope | [6 empty] | 5.3, 5.4
|  | 8.1. | consider factors that may influence the scope, such as: boundaries of the area, in-scope versus out-of-scope locations, subprocesses, components of the process, timeframe, etc. | [5 empty] | 5.3
|  | 8.2. | review once more the "Planning Considerations" and "Establish the Engagement Objectives" to attain an understanding of the key risks identified during planning phase | [5 empty] | 5.3
|  | 8.3. | describe what will be and what it will not be included in the engagement scope | [5 empty] | 5.3
|  | 8.4. | review the established objectives to be sure that all the engagement objectives can be accomplished under the defined scope. | [5 empty] | 5.3
|  | 8.5. | disclose any scope limitation and any request from the auditee or senior management related to items to be included or excluded from engagement scope | [5 empty] | 5.4
|  | 8.6. | disclose the reliance on others work, if case | [5 empty] | 5.3
RESOURCE DEPLOYMENT | 9. | Resource Allocation | [6 empty] | 7.2, 7.4
|  | 9.1. | review the engagement objectives and engagement scope for resource allocation purposes | [5 empty] | 7.4
|  | 9.2. | from previous discussions with stakeholders identify the nature and complexity of the engagement | [5 empty] | 7.4
|  | 9.3. | perform an inventory of the necessary resources: staff, technology and other | [5 empty] | 7.4
|  | 9.4. | assign the staff to the engagements based on their availability, knowledge, skills and experience | [5 empty] | 7.2, 7.4
|  | 9.5. | discuss with the staff any concerns related to the resources allocated to the engagement | [5 empty] | 7.4
|  | 9.6. | decide if external resources are necessary to fill in the gaps | [5 empty] | 7.4
|  |  | 9.6.1. | consider whether additional training is an option |  |  |  |  | 7.4
|  |  | 9.6.2. | consider if closer supervision would be appropriate |  |  |  |  | 7.4
|  |  | 9.6.3. | consider supplementing existing resources with other options, such as using guest auditors, employing a subject matter expert or co-sourcing |  |  |  |  | 7.4
ISSUING THE AUDIT PROGRAMME | 10. | Design the Engagement Work Programme | [6 empty] | 7.2
|  | 10.1. | review the engagement objectives and engagement scope | [5 empty] | 7.2
|  | 10.2. | design the risk and control matrix | [5 empty] | 7.2
|  | 10.3. | consider aspects of the engagement, as: | [5 empty] | 7.2
|  |  | 10.3.1. | appropriate sample size for testing and methodologies used |  |  |  |  | 7.2
|  |  | 10.3.2. | the scope of the engagement |  |  |  |  | 7.2
|  |  | 10.3.3. | how the engagement objectives will be achieved |  |  |  |  | 7.2
|  |  | 10.3.4. | if necessary resources are available |  |  |  |  | 7.2
|  |  | 10.3.5. | nature, extent and timing of the audit tests |  |  |  |  | 7.2
|  | 10.4. | the engagement work programme should communicate roles, responsibilities and tasks to the members of the engagement team | [5 empty] | 7.2